## Example
EXAMPLE Budgeting Process for Oct. through Sept. Fiscal Year |  |  | Revised Month YEAR
General Policy: ORG will strive to create balanced budgets that feature realistic revenue projections and conservative expense projections. Income and expenses will include the budget impact of strategic initiatives. The balanced budget will include depreciation expense and an amount to increase the operating reserve as determined by ORG's multi-year capital budget.
DATES | TASKS / MEETINGS | LEADER RESPONSIBLE / BOARD & STAFF PARTICIPANTS | NOTES
April
1 - 7 | Provide departmental budget worksheets to department heads. | Finance Manager | Work sheets include prior year balances and current year-end projections.
1 - 30 | Review mission and strategic plan. | Finance Committee, ED, Finance Manager | Ensure that all strategic initiatives with budget impact are included in budget process.
14 | Board Meeting - confirm budget year strategic goals. | Board Chair, ED, board members
1 - 30 | Begin to develop programming schedule. | Program Directors | Anticipate special costs.
May
1 - 31 | Develop Contributed Revenue projections; update annual fundraising plan. | Board FR Cmte, ED, Finance Manager | Use work sheets and budget template detail tabs and fundraising plan.
17 | Joint meeting with Finance and Resource Development Committee | Board Finance Cmte & FR Cmte, ED, Finance Manager | To confirm and commit to Contributed Revenue Plan.
1 - 31 | Update multi-year and capital goals. | ED, Finance Manager | Refer to strategic plan.
1 - 31 | Develop Earned Revenue projections based on programming schedule. | ED, Finance Manager | Use work sheets and budget template detail tabs
June
1 - 21 | Prepare Detailed Expense projections. | All Dept. heads, Dev. Team, Dir, and Finance Manager | Use work sheets and budget template detail tabs
22 - 30 | Assemble Draft Budget and Narrative. | Directors, Finance Manager | Use Budget Template - all tabs.
July
1 - 4 | Send draft budget and narrative to finance committee members. | Finance Manager | Draft budget includes at least one year of history plus current year end projections for context.
12 | Finance Cmte Meeting to discuss draft budget | Treasurer, Finance Committee, ED, Finance Manager | Include discussion of multi-year targets, capital expenses, and strategy confirmation.
15 - 27 | Revise budget per results of finance cmte meeting; send to cmte for final review. | ED, Finance Manager | Run any changes to FR portion by FR Cmte
27 - 31 | Finance Cmte members review revised budget and provide any new feedback. | Finance Cmte | Schedule additional finance cmte meeting, if necessary.
August
1 - 5 | Make changes (if any) to budget. | Directors, Finance Manager
5 - 7 | Send final proposed budget and narrative to finance cmte. | Finance Manager | Last chance for changes.
7 - 10 | Circulate proposed budget with narrative to all board members. | Finance Manager | Should be at least one week before board meeting. Send only GL budget tab, and selected detail (fund raising).
27 | Board Meeting: Board discusses and approves budget. | Treasurer, Board Members, Director, Finance Manager | Budget is presented to the board by the Treasurer.
Sept.
1 - 15 | Make last changes (if any) to budget.
30 | Fiscal Year Ends
Variance Policy: Department heads have discretion to repurpose expenses between line items within their purview as long as the result does not exceed the approved total for the department. Should an overage be anticipated, the department head should inform the director to see if the overage can be mitigated or absorbed by another department. Any expected overage of more than XX % must be reported to the finance committee for approval.
Reporting: Monthly financial statements will include revised year-end projections that reflect expected changes from the original income and expense budget projections, both positive and negative, with brief narrative explanations.
Cash Flow: In addition to being allocated by functional activity, the budget should be estimated on a cash flow basis by month and entered into QuickBooks by month per line item to assist with producing year-end projections and in monitoring cash flow.
Prepared by Elizabeth Hamilton Foley © 2021
This document is provided for small and midsize nonprofit organizations for educational purposes only. It should not be considered legal or accounting advice on any specific matter. The user of this template/sample is responsible for tailoring the contents to meet the specific needs and circumstances of the organization. It is recommended that all policies be reviewed by legal counsel familiar with the laws of the state in which the nonprofit conducts business. The user is responsible for double checking all calculating formulas.

## Blank Template
ORG Budgeting Process for _____ through _____ Fiscal Year |  |  | Revised __________________
General Policy:
DATES | TASKS / MEETINGS | LEADER RESPONSIBLE / BOARD & STAFF PARTICIPANTS | NOTES
Variance Policy:
Reporting:
Cash Flow:
Other: