## DETAIL
ORG Budgeting Process for January through December Fiscal Year |  |  | REV: DATE
Meetings | Deadline Dates | See general budgeting principles at bottom.
DATES | TASKS / MEETINGS | LEADER RESPONSIBLE / BOARD & STAFF PARTICIPANTS | NOTES
Mar - May | Develop Strategic Focus ~ Board & Staff
3/1 - 5/19 | Develop strategic focus areas for upcoming budget year; confirm with board | Executive Director (ED), Board, finance team and program team | Confirm planned program alignment with strategic goals
5/26 Retreat | Present, review, confirm mission and strategic plans for budget year at Board Retreat | ED, Program Director (PD), Director of Finance (DF), department leaders, Board members | Ensure that all strategic initiatives with budget impact are included in budget process.
June | Confirm Strategy / Plan Programming / Projections
5 - 7 | 3-day departmental Strategic Focus Retreat | DP, DF, program / department leaders | Facilitated retreat to confirm program and operations plans for upcoming year per board retreat.
9 - 20 | Provide prior year & year-to-date departmental reports to program & management depts. | DF, with finance team assistance as assigned to meet with staff to review reports. | Include all detail and year-to-date cumulative data for use in creating year-end projections. Finance team meetings with staff to confirm/correct coding and answer questions.
20 - 30 | Update year-end projections for current year. | DP, DF, with assistance from participants as assigned | Finance team to meet with staff to assist with projections process.
July | Continue Programming Planning / Projections
1 - 15 | Continue work on year-end projections and program planning. | DP, DF, with assistance from participants as assigned | Projections are needed for grant reports due by/before 7/31 and for budgeting process.
5 - 31 | Develop programming schedule and partner selection. | DP, DF, with assistance from participants as assigned | Anticipate special costs.
11 | Program Departmental Meeting / Budget Process check-in | DP & participants as assigned
15 | Year-end projections DUE to Finance team. | DP, DF, with assistance from participants as assigned | Preliminary submission for review and comment by finance team and DP.
15 - 24 | Finance team and DP review, question, confirm projections. Finalize by 7/24. | DP, DF, with assistance from participants as assigned | Finalize by 7/24.
25 | Program Departmental Meeting / Budget Process check-in | DP & participants as assigned
August | Resource Development & Spending Plans
1 | Provide updated departmental budget workbooks to department leaders. | DF, with assistance as assigned
1 - 31 | Develop contributed revenue projections; update annual fundraising plan. | Board fundraising committee, ED, with assistance & participants as assigned | Use work sheets and budget template detail tabs and fundraising plan. Plans should include info on what program and other costs can be covered by which grants.
1 - 31 | Begin detailed expense budgets and personnel planning. | ED, DF, department leaders | Program leaders should meet frequently to share plans and ensure synergy among programs and shared expenses such as transportation, food, space use, etc. Use work sheets and budget template detail tabs.
1 - 31 | Update multi-year capital goals. | Department leaders | Refer to strategic plan.
1 - 31 | Develop earned revenue projections based on programming schedule. | ED, DF, DP, with assistance from participants as assigned | Use work sheets and budget template detail tabs
8 | Training Meeting for staff on use of budget workbooks | DF, & participants as assigned
10 | Program Departmental Meeting / Budget Process check-in | DP & participants as assigned
22 | Program Departmental Meeting / Budget Process check-in | DP & participants as assigned
Sept | Budget Adjustments & Narrative
1 - 9 | Continue detailed expense and earned revenue projections. | Department leaders | Use work sheets and budget template detail tabs. Confer with resource development folks to understand what expenses are covered by which dedicated funding.
1 - 9 | Continue contributed revenue projections. | Board fundraising committee, ED, with assistance from participants as assigned | Use work sheets and budget template detail tabs
1 - 9 | Develop Exec, G&A, and Staffing Plan budgets | ED, with assistance from participants as assigned
11 | Submit 1st draft departmental workbooks to finance team. | Department leaders
12 | Joint meeting of Board Finance and Fundraising Committee to confirm budget fundraising plan. | Treasurer, finance and fundraising committees, ED, DF, staff fundraising team | Board level acceptance of fundraising plan and board role in achieving the objectives.
13 - 16 | Assemble Draft Budget. | DF, finance team as assigned | Use Budget Template - all tabs. Update Contributed Revenue tab per Joint Meeting results as necessary.
19 | Send preliminary budget draft to staff leaders. | DF | For review and prep for staff budget meeting. Complete month-over-month (cash flow) for all budget items.
19 | Last Staff Budget Meeting to make budget adjustments if/as necessary | ED, finance team and department leaders | Confirm agreement on what program and other costs can be covered by which grants.
19 - 25 | Draft budget Narrative document. | ED, DP, DF, with assistance as assigned | See prior year versions to update graphs and trend data, etc.
22 - 25 | Implement budget revisions from staff | DF, finance team as assigned
27 | Send draft budget and narrative to finance committee members. | DF | Draft budget includes at least one year of history plus current year end projections for context. Provide comparative ($ and %) between YE Projection and proposed budget.
Oct | Review Budget Drafts
4 | Finance Committee Meeting to discuss draft 1 of the budget | Treasurer, finance committee, ED, finance team
5 - 14 | Revise budget if necessary per results of finance committee meeting; send to committee for final review. | ED, DF | Run any changes to contributed revenue portion by fundraising committee
5 - 14 | Finalize Narrative | ED, DF, with assistance as assigned
14 - 18 | Finance committee members review revised budget and provide any new feedback. | Finance committee | Schedule additional finance committee meeting, if necessary.
14 - 24 | Update year-end projections. | ED, DF, DP, with assistance from participants as assigned | Update or confirm year-end spending expectations. Use latest YTD departmental reports.
24 | Revised year-end projections due to Finance Team | ED, DF, DP, with assistance from participants as assigned
18 - 24 | Make any additional changes from finance committee to budget. | ED, DP, DF
25 | Send final proposed budget and narrative to finance committee. | ED, DP, DF
Nov | Finalize Budget ~ Finance Committee Approval
1 | Finance Committee Meeting to finalize draft budget | Treasurer, finance committee, ED, DF | Last chance for changes to numbers.
2 - 18 | Last update of year-end projections. | ED, DF, DP, with assistance from participants as assigned | Update or confirm year-end spending expectations. Use latest YTD departmental reports.
29 | Finance Committee Meeting to finalize narrative for budget | Treasurer, finance committee, ED, DF | Last chance for changes to narrative.
Dec | Board Approval
2 | Circulate finalized budget to all board members (if any changes we made). | ED, DP, DF
8 | Board Meeting: Board discusses and approves budget. | Treasurer, Board Members, ED | Budget is presented to the board by the Treasurer.
12 - 16 | Add any budget changes from board meeting to workbooks and aggregate budget | DF | Finalize month-over-month (cash flow) in the budget workbooks; Transfer to the aggregate budget doc.
16 | Return edited workbooks to departments | DF
31 | Fiscal Year Ends
Jan | Roll Forward
2 - 29 | Enter by-month budgets into accounting system | DF | In time to use for January internal reports.
General Policy: ORG will strive to create balanced budgets that feature realistic revenue projections and conservative expense projections. Income and expenses will include the budget impact of strategic initiatives. Budgets will follow appropriate cost principles for federal grants as appropriate. The balanced budget will include depreciation expense and an amount to increase the operating reserve as determined by ORG's multi-year capital budget.
Variance Policy: Chiefs have discretion to repurpose expenses between line items within their purview as long as the result does not exceed the approved total for the department. Should an overage be anticipated, the chief should inform the executive director to see if the overage can be mitigated or absorbed by another department and/or is allowable under relevant grant terms.
Reporting: Monthly financial statements will include revised year-end projections that reflect expected changes from the original income and expense budget projections, both positive and negative, with brief narrative explanations.
Month-over Month: In addition to being allocated by functional activity, the budget should be estimated on a month by month basis per line item to assist with producing year-end projections and in monitoring cash flow.

## SUMMARY
ORG Budgeting Process for January through December Fiscal Year |  |  | REV: DATE
Meeting & Deadline Dates
DATES | TASKS / MEETINGS | LEADER RESPONSIBLE / BOARD & STAFF PARTICIPANTS | NOTES
Mar - May | Develop Strategic Focus ~ Board
4/1 - 5/31 | Develop strategic focus areas for upcoming budget year; confirm with board | Executive Director (ED), Board, finance team and program team | Confirm planned program alignment with strategic goals
June | Confirm Strategy / Plan Programming / Projections
27 -28 | 3-day departmental Strategic Focus Retreat | DP, DF, department leaders | Facilitated retreat to confirm program and operations plans for upcoming year.
July | Continue Programming Planning / Projections
1 - 15 | Continue work on year-end projections and program planning. | DP, DF, with assistance from participants as assigned | Projections are needed for grant reports due by/before 7/31 and for budgeting process.
5 - 31 | Develop programming schedule and partner selection. | DP, DF, with assistance from participants as assigned | Anticipate special costs.
August | Resource Development & Spending Plans
1 - 31 | Develop contributed revenue projections; update annual fundraising plan. | Board fundraising committee, ED, with assistance & participants as assigned | Use work sheets and budget template detail tabs and fundraising plan. Plans should include info on what program and other costs can be covered by which grants.
1 - 31 | Begin detailed expense budgets and personnel planning. | ED, DF, department leaders | Program leaders should meet frequently to share plans and ensure synergy among programs and shared expenses such as transportation, food, space use, etc. Use work sheets and budget template detail tabs.
Sept | Budget Adjustments & Narrative
1 - 9 | Continue detailed expense and revenue projections | All relevant staff and board committees | Use work sheets and budget template detail tabs. Confer with resource development folks to understand what expenses are covered by which dedicated funding.
12 | Joint meeting of Board Finance and Fundraising Committee to confirm budget fundraising plan. | Treasurer, finance and fundraising committees, ED, staff fundraising team | Board level acceptance of fundraising plan and board role in achieving the objectives.
19 | Last Staff Budget Meeting to make budget adjustments if/as necessary | ED, DP, DF, finance team and department leaders | Confirm agreement on what program and other costs can be covered by which grants.
27 | Send draft budget and narrative to finance committee members. | DF | Draft budget includes at least one year of history plus current year end projections for context. Provide comparative ($ and %) between YE Projection and proposed budget.
Oct | Review Budget Drafts
4 | Finance Committee Meeting to discuss draft 1 of the budget | Treasurer, finance committee, ED, finance team
14 - 24 | Update year-end projections. | ED, DF, DP, with assistance from participants as assigned | Update or confirm year-end spending expectations. Use latest YTD departmental reports.
25 | Send final proposed budget and narrative to finance committee. | ED, DP, DF
Nov | Finalize Budget ~ Finance Committee Approval
1 | Finance Committee Meeting to finalize draft budget | Treasurer, finance committee, ED, finance team | Last chance for changes.
2 - 18 | Last update of year-end projections. | ED, DF, DP, with assistance from participants as assigned | Update or confirm year-end spending expectations. Use latest YTD departmental reports.
29 | Finance Committee Meeting to finalize narrative for budget | Treasurer, finance committee, ED, DF | Last chance for changes.
Dec | Board Approval
2 | Circulate finalized budget to all board members (if any changes we made). | ED, DP, DF
8 | Board Meeting: Board discusses and approves budget. | Treasurer, Board Members, ED | Budget is presented to the board by the Treasurer.
12 - 16 | Add any budget changes from board meeting to workbooks and aggregate budget | DF | Finalize month-over-month (cash flow) in the budget workbooks; Transfer to the aggregate budget doc.
31 | Fiscal Year Ends
Jan | Roll Forward
2 - 29 | Return updated departmental workbooks to staff; Enter by-month budgets into QB | DF | In time to use for January internal reports.
General Policy: ORG will strive to create balanced budgets that feature realistic revenue projections and conservative expense projections. Income and expenses will include the budget impact of strategic initiatives. Budgets will follow appropriate cost principles for federal grants as appropriate. The balanced budget will include depreciation expense and an amount to increase the operating reserve as determined by ORG's multi-year capital budget.
Variance Policy: Chiefs have discretion to repurpose expenses between line items within their purview as long as the result does not exceed the approved total for the department. Should an overage be anticipated, the chief should inform the executive director to see if the overage can be mitigated or absorbed by another department and/or is allowable under relevant grant terms.
Reporting: Monthly financial statements will include revised year-end projections that reflect expected changes from the original income and expense budget projections, both positive and negative, with brief narrative explanations.
Month-over Month: In addition to being allocated by functional activity, the budget should be estimated on a month by month basis per line item to assist with producing year-end projections and in monitoring cash flow.